# Annex No. 1: Technical Specifications and Evaluation Questions

## Context

The objective of the public procurement is to commission an independent evaluation of the project 'Sustainable Landscape through Integrated Management (SLIM)'. The project is implemented by the Czech Development Agency with support from the European Union, Sweden, and the Czech Republic. The project commenced in October 2023 and will conclude in September 2027. The project is operating with a budget totaling 7 million EUR.

SLIM is part of the wider EU Green NEXUS Programme, alongside three other projects: the GIZ-led AWARE 2.0, the WFP-led ELSAM, and a forthcoming fourth component. The role of SLIM within the programme is to facilitate the organization of ILM steering meetings and working groups, create M&E methodologies for the ILM/Nexus, and promote ILM mainstreaming and participatory planning. Furthermore, it is responsible for establishing inter-institutional partnerships and supporting Nexus implementing partners' meetings to ensure smooth coordination and implementation of activities.

SLIM works in close collaboration with the Ministry of Finance and National Planning (MoFNP), the Ministry of Green Economy and Environment (MGEE) – Forestry Department, and the Ministry of Technology and Science (MoTS) – National Remote Sensing Centre (NRSC).

The project is designed to achieve two primary outcomes:

- Strengthened governance mechanisms, policies, and coordination frameworks for integrated landscape management (ILM) and climate adaptation.

- Enhanced technical and technological capacities for ILM and climate adaptation among stakeholders.

To achieve the project Outputs and their indicators, the project focuses on: (a) the development and mainstreaming of ILM, (b) strengthening inter-institutional linkages, (c) developing data products for evidence-based decision-making, and (d) providing comprehensive technical assistance and capacity building.

## Specific objectives of the Evaluation

- Assess the performance of the project against the logical framework and theory of change, paying attention to the flow of results linking them.

- Evaluate the level of ownership of decision-makers and extent to which the project interventions were aligned with the priorities and context of beneficiaries and respond to their needs.

- Assess the extent to which project outcomes are likely to be sustained beyond the project duration and with continued support from relevant stakeholders.

- Identify lessons learned from the project implementation and identify deficiencies and “blind spots” in processes and propose corrective actions for the remaining project period.

- Evaluate the effectiveness of Green Nexus programme partners cooperation and impact on the implementation.

## Evaluation Criteria

The Contractor is required to evaluate the project based on the following international criteria:

- Relevance: The extent to which the intervention objectives and design respond to beneficiaries’ and partner/institution needs, policies, and priorities, including in light of evolving needs and priorities.

- Coherence: The compatibility/complementarity of the intervention with other interventions in Zambia and other funders.

- Effectiveness: Assess progress: the extent to which the intervention achieved, or is expected to achieve, its objectives, and its results, including any differential results across groups.

- Efficiency: The extent to which the intervention delivers, or is likely to deliver, results in a cost effective and timely use of resources.

- Impact:  The assessment of early indications of higher-level effects and the likelihood that the intervention will generate significant intended or unintended long-term changes, based on available evidence and emerging results.

- Sustainability: The extent to which the net benefits of the intervention continue or are likely to continue and promote long-term impact.

## Key guiding evaluation questions

- To what extent has the project efficiently and effectively contributed to the integration of the ILM approach into policies, regulations, and other relevant policy instruments?

- How effective has the project been in establishing and maintaining partnerships that actively support ILM mainstreaming at national and subnational levels, including evidence-based examples of achievements?

- How efficient and effective have the capacity-building activities been in strengthening evidence-based decision-making and the use of data among key stakeholders?

- To what extent has the project generated direct and indirect impacts on policies, regulations or strategic documents in relevant thematic areas?

- What have been the main challenges encountered in project implementation, and how have they influenced progress toward intended results?

- What is the level of awareness, ownership and engagement of key decision-makers and administrative structures in ILM and related processes?

- How effective are the current collaboration and coordination mechanisms in supporting ownership and long-term sustainability of data products and ILM tools?

- To what extent has staff turnover among trained professionals affected the technical and technological capacities of institutions and the long-term sustainability of ILM-related skills?

- To what extent has cooperation among Green Nexus Programme Partners contributed to project SLIM implementation and delivery of results?

- How efficiently and effectively SLIM has promoted ILM, monitor and reported on ILM results?

## The evaluation will furthermore assess:

- Gender inclusion throughout project implementation

  - The extent of the activities impact on gender inclusion through reports on gender disaggregated achievements and data.

## Scope of the evaluation

The evaluation will cover the period from October 2023 to January 2026 and will assess progress made towards the achievement of the project objectives and expected results as outlined in the project log frame; the extent to which they were achieved and the contributing factors affecting the achievement of the intended results; leading to recommendations for ensuring the final targets in the log frame will be reached by end of the project.

The total duration of the assignment is 3 months from the effective date of the Contract. This period includes all preparation, the field mission, drafting of reports, and the incorporation of feedback from the CzDA.

Deliverables:

  - The Inception Report

- It will outline the proposed evaluation methodology, including the alignment of methods with the evaluation questions and criteria. It will also contain a binding timetable for the evaluation, including the implementation schedule for the field mission and interviews.

- The report will be created remotely without requiring physical presence in the project location and submitted to CzDA within 10 days of the contract signing.

  - The Mid-term Evaluation Report

- The evaluation report will include a main report – no more than 25 standard pages in English, and a management summary, no more than 4 standard pages in English.

- The report will include a summary of key background information about the evaluated project context, applied evaluation methodology, summary of main findings, reflection on the main evaluation questions, presentation of independent findings, conclusions, and resulting recommendations.

- In order to prepare the report, the evaluation team will conduct primary data collection in the project location, Lusaka (and surrounding area), Zambia, over an estimated period of 10 days.

- The Mid-term Evaluation Report will be created remotely without requiring physical presence in the project location submitted to the CzDA within two weeks after the field mission is completed.